For this tender, prepare the live demo as a technical working session, not another proposal presentation. GovTech says the live demonstration is approximately 20 minutes + 10 minutes Q&A, must be led personally by the Tech Lead named in the Tender Offer, and should focus principally on actual technical work and engineering practice.

The most important requirement is to demonstrate an end-to-end flow from understanding an existing system/requirement, through specification, implementation/prototype, and verification. If AI/automation is used, the Tech Lead needs to explain its function, inputs/outputs, where human engineering judgement remains, and how outputs are validated.

Recommended 20-minute demo

| Slide | Content | Time | What to Cover / Demonstrate |
| --- | --- | --- | --- |
| 1 | USER Introduction & Tech Lead | 30 sec | Brief USER credentials; introduce Tech Lead and role in the demonstration |
| 2 | Demo Scenario & Objective | 30 sec | What application/component is being demonstrated, the problem/change requirement and intended outcome |
| 3 | Technical Context / Architecture | 1 min | Existing system/component, architecture, key dependencies, constraints and repository/application structure |
| 4 | Engineering Workflow & AI/Human Controls | 1 min | Introduce the flow: Analyse → Specify → Implement → Verify → Trace; briefly explain where AI assists and where engineers review/decide |
| 5 | Live Technical Demo | 15 min | Hands-on demonstration detailed below |
| 6 | Traceability & Verification Summary | 1.5 min | Show complete chain: Finding/Requirement → Specification → Implementation → Test → Verification Evidence |
| 7 | Closing / Transition to Q&A | 30 sec | Summarise outcome, AI contribution and human engineering decision/validation |
|  | Total Live Demo | 20 min | Followed by approximately 10 min Q&A |

15min Live Tech Demo

| Duration | Live Demonstration | What GovTech Sees |
| --- | --- | --- |
| 3 min | Current-State Analysis | Tech Lead examines code/system behaviour, uses AI/tooling where relevant, identifies business logic/dependencies and distinguishes evidence from assumptions |
| 2.5 min | Specification Development | Translate validated findings/change requirement into structured, version-controlled specification with expected behaviour and acceptance criteria |
| 5 min | Specification-Driven AI-Assisted Engineering | Use specification as engineering input; demonstrate GitHub Copilot/AI assistance; inspect generated output; Tech Lead reviews, challenges and refines it before acceptance |
| 4.5 min | Verification & Consistency | Run tests; compare expected vs actual behaviour; where relevant compare existing vs replacement behaviour; show verification evidence and treatment of discrepancies |
| Total |  | 15 min |

This directly matches GovTech's requirement that the demo show progression from existing system/requirement → specification → implementation/prototype → verification.

What to would prepare:

Use one small but technically credible application/component rather than trying to demonstrate RWS, DSBJ and AbbVie. GovTech explicitly permits an existing/completed implementation or a representative environment that reasonably demonstrates your capability; you do not need to build a new solution solely for the tender. Sanitisation is also expressly permitted.

Prepare these in advance:

- A small repository that the Tech Lead genuinely understands.

- Existing code with enough complexity to analyse a business rule/dependency.

- A clear change requirement or modernisation problem.

- Current-state evidence and a deliberately documented assumption/uncertainty.

- Version-controlled Markdown specification.

- Acceptance criteria and expected behaviour.

- GitHub Copilot/approved AI-assisted engineering environment.

- A controlled implementation change.

- Automated tests.

- Verification results/evidence.

- Git history/PR or equivalent showing the change.

- A simple traceability view connecting requirement/specification/code/test.

- One architecture diagram only if needed to orient GovTech.

- Sanitised data and no confidential client source code.

This also aligns with GovTech's broader specification-driven requirement: specifications or equivalent structured descriptions should actively inform both implementation and verification, with traceability to current-state findings, changed requirements and verification evidence.

The Tech Lead needs to be ready for the Q&A

This is especially important. GovTech may direct questions personally to the Tech Lead about the technical approach, tooling, degree of automation, technical decisions, limitations and relevance of the demonstrated work.

- I would rehearse questions such as:

- Why did you conclude this is the actual current-state behaviour?

- What if documentation contradicts the source code?

- Why did you choose this modernisation approach?

- How do you know the AI-generated code is correct?

- What information was supplied to the AI?

- What does the engineer check before accepting its output?

- How is the specification versioned?

- How does the same specification inform testing?

- What happens when a requirement changes?

- How would you establish behaviour if source code were unavailable?

- How would you perform consistency verification between legacy and replacement behaviour?

- What are the limitations of your analysis? What happens if GovTech does not approve the proposed AI tool?

One important point: don't make the live demo just GitHub Copilot generating code. The tender places particular emphasis on specification-driven development, and GovTech evaluates the underlying engineering judgement and human controls—not ownership or sophistication of the AI tool itself.

For USER, I would build the live demo around a very clear story:

Existing System → Evidence-Based Analysis → Version-Controlled Specification → GitHub Copilot-Assisted Implementation → Engineer Review → Automated Verification → Traceability

That is much closer to what GovTech is asking to evaluate than demonstrating lots of different AI tools.

| Target | Activity | Key Output / Owner |
| --- | --- | --- |
| 29 Sep–1 Oct | Demo Planning & Scope Lock | Confirm Danilo as Tech Lead; select one representative demo scenario; lock the story: Current State → Specification → AI-Assisted Implementation → Human Review → Verification → Traceability; assign supporting team |
| 2–4 Oct | Demo Environment & Scenario Build | Prepare sanitised application/repository, current-state code, change requirement, Markdown specification, AI tooling, test cases and verification approach |
| 4 Oct | Scenario & Technical Review | Confirm scenario demonstrates current-state analysis, specification-driven development, AI/human interaction, consistency verification and traceability |
| 5–7 Oct | Build Working Demo + Slides | Complete working demo while preparing the 7-slide deck: USER/Tech Lead; Scenario; Architecture; Engineering Workflow; Live Demo; Traceability; Closing |
| 7 Oct | Demo Content Freeze | Lock the main scenario and demonstration sequence. Avoid introducing new functionality unless required to fix an issue |
| 8 Oct | Technical Review #1 | Architects/developers challenge Danilo on current-state findings, assumptions, specifications, AI inputs/outputs, engineering decisions, verification and limitations |
| 9 Oct | Rehearsal #1 – End-to-End Run | First timed 20-min demo + 10-min Q&A. Validate 3 min slides + 15 min live technical demo + 2 min summary. Target completion within 18–19 min |
| 10–11 Oct | Refinement & Q&A Preparation | Fix technical issues; simplify transitions; strengthen Requirement/Finding → Specification → Code → Test → Evidence traceability; prepare likely GovTech technical questions and responses |
| 12 Oct | Rehearsal #2 – Technical Panel | Internal technical panel challenges Danilo as GovTech evaluators would: architecture, source-code analysis, AI controls, specification management, testing, consistency verification, security and limitations |
| 13 Oct | Rehearsal #3 – Management / Evaluation Panel | Full presentation with less scripted Q&A. Check clarity for evaluators who may not know the demo application. Supporting team practises when to step in |
| 14 Oct | Final Content Freeze | Freeze slides, code, specification, test cases and demo data. Only critical fixes after this point |
| 15 Oct | Rehearsal #4 – Final Dress Rehearsal | Run under actual presentation conditions: screen sharing, laptop, IDE, browser, GitHub Copilot, test execution and slide/demo transitions. Full 20 + 10 min session |
| 16 Oct | Backup & Contingency Check | Prepare backup laptop/environment, local repository, PDF slides, backup screenshots/video of critical steps, credentials/access, charger/adapters and offline evidence |
| 3rd Week Oct | Live Technical Demo | Danilo leads the technical demonstration; supporting team attends as permitted and supports Q&A |

Slides: ~3–4 minutes total
Hands-on technical demonstration: ~14–15 minutes
Closing/traceability: ~1–2 minutes

Don't make it a 20-minute slide presentation. GovTech says the demonstration should focus principally on technical work and actual engineering practice and particularly on specification-driven development.

For the slides, to prepare only:

| Slide | Content | Time |
| --- | --- | --- |
| 1 | USER Introduction & Tech Lead | 30–45 sec |
| 2 | Demo Scenario & Objective | 45 sec |
| 3 | Technical Context / Architecture | 1 min |
| 4 | Engineering Workflow & AI/Human Controls | 1 min |
| 5 | Live Technical Demo | ~14–15 min |
| 6 | Traceability & Verification Summary | 1–2 min |
| 7 | Closing / Q&A | Very brief |

The live environment, rather than the slides, should demonstrate the actual code, specification, AI-assisted workflow, engineer review, tests and verification evidence.